## IMS_System
Inventory Management System Module
[Schedule of Works]
Sr. # | Description | Date | Remarks | Hours
1 | Initial layout of Dashboard + Report Requirement | 16 - 11 - 2019 | Done | 2
2 | Data input module | 17 - 11 - 2019 | Done | 2
3 | Linking and testing | 18 - 11 - 2019 | Done | 2
4 | General updates | 19 - 11 - 2019 | Done | 1
5 | General updates | 20 - 11 - 2019 | Done | 1
6 | First revision preparation | 21 - 11 - 2019 | Done | 1.5
7 | First revision preparation | 22 - 11 - 2019 | Done | 1.5
8 | First revision sent | 23 - 11 - 2019 | Done | 2
9 | Second revision based on lot of input - Ongoing | 26 - 11 - 2019 | Done | 3
10 | Second revision based on lot of input - Sent | 29 - 11 - 2019 | Done | 3
11 | Further input and revision 03 works | 30 - 11 - 2019 | Done | 1.5
12 | Many features added for reporting - Rev03 sent | 02 - 12 - 2019 | Done | 4
13 | Updates based on comments | 04 - 12 - 2019 | Done | 2
14 | Lot of feature updates and reports update | 07 - 12 - 2019 | Done | 5
15 | Preparation for actual data input | 08 - 12 - 2019 | Done | 3
16 | Sent Rev-04 with most parts working | 12 - 12 - 2019 | Done | 2
17 | Revision-05 due to some generic comments | 30 - 12 - 2019 | Done | 3
18 | Revision-06 - Bug fixes | 31 - 12 - 2019 | Done | 1
19 | Revision-07 - Previous file check & bug fixes | 02 - 01 - 2020 | Done | 1
20 | Revision-08 - Re-import related issues | 05 - 01 - 2020 | Done | 1
21 | Revision-09 _ Over-ride function added | 07 - 01 - 2020 | Done | 1.5
22 | Revision-10_File duplicate checks & Date related | 13 - 01 - 2020 | Done | 2
23 | Revision-11_File duplicate checks updated | 16 - 01 - 2020 | Done | 1
47